GoSit deployment plan and cost estimate

Prepared 26 October 2026 for 11419056 Canada Inc., operating as GoSit

The short version Today only the public website is online. It sits at www.gosits.com on Azure's free tier. The API, the database, the family and caregiver app, and the admin tools all run only on your computer. The database you have working is on your computer too. A website on the internet cannot reach it. So the contact form, parent and caregiver sign-up, and the Certn connection all need one thing first: a small online server and database in Azure. Cost for that: about CAD 45 to 70 a month, before tax and before the outside services listed in section 4 (Stripe, Certn, email, and so on). Nothing has been created yet. I need your go-ahead (section 7).

# 1. The address map

| Address | What it is for | Where it runs | Status |
| --- | --- | --- | --- |
| www.gosits.com (and gosits.com) | Public website, with the contact form | Azure Static Web Apps (free) | Live now. The form comes in phase 2. |
| api.gosits.com | The backend and database. Mobile apps, Stripe and Certn talk to it. | Azure Container Apps + Postgres | Phase 1 |
| app.gosits.com | Families and caregivers sign up, book, and message | Azure Container Apps | Phase 3 |
| admin.gosits.com | Your staff: checks, disputes, incidents, enquiries | Same app as above, chosen by address | Phase 3 |

Add the DNS records for api, app and admin only after each server exists. An address that points at nothing can be taken over by someone else.

# 2. The plan, in order

## Phase 1: Put the backend and database online (private for now)

- Create a PostgreSQL database in Azure (Canada Central), with automatic backups on.

- Package the API and run it as an always-on container. It must stay on because it runs background jobs: booking sweeps, payout sends, email delivery.

- Keep every secret (database password, token signing key, Stripe, LiveKit, Certn) in Azure Key Vault, not in the code.

- Set a new, strong token signing key and fix the placeholder token issuer (`api.gosit.ca`) to `api.gosits.com`.

- Run the admin account set-up once, so your staff can sign in to admin.

- Keep Stripe in test mode. Real money does not move in this phase.

- Add the DNS records at GoDaddy for api.gosits.com. Azure then issues the certificate by itself.

Two backend items I would skip for now. The templates already in the project also create a Redis cache (about CAD 23 a month) and a Service Bus (about CAD 15). Nothing in the code needs either yet, so leaving them out keeps the bill lower. We can add them later.

## Phase 2: Replace the email buttons with a contact form that saves to the database

- A form on the public site: name, email, who you are (family, caregiver, partner or vendor), a message, and a consent line. No sensitive details are asked for.

- It saves each enquiry to a new table in the database, and your staff read them in an admin page, where they mark each one handled. You can also be emailed when one arrives.

- Built-in protection against spam: a hidden trap field and a limit on how many a person can send.

- The website is a separate site from the API, so the API must be told to accept this one form from www.gosits.com, and nothing else.

- This needs phase 1 first. I can build and test it on your computer before then.

## Phase 3: Put the family and caregiver app online, with the admin address

- Package the web app and run it as a container. The web app needs to know the API address at build time, so it is built after phase 1.

- Serve admin.gosits.com from the same container, and show only the staff pages on that address.

- Set up outgoing email (password resets, verification, booking notices) through an email service with your domain verified, so messages do not land in spam. The backend is already built for this and expects an outside email relay (Brevo by default).

- Option for staying private: deploy with sign-up closed so only you and invited testers can get in. That switch does not exist yet. I would add it. It is a small change and it is the safe way to be "live for us" while legal work finishes.

## Phase 4: Connect Certn for caregiver background checks

See section 6. This can be built against Certn's testing environment as soon as they give you a test key, before your account is fully approved.

## Phase 5: Opening registration to the public

Only after the checklist in section 5 is done. This is a decision for you, not a technical step.

# 3. Things I checked in the code that affect deployment

- The browser never calls the API directly for sign-in and bookings. The web app's own server does. So the app needs no cross-site setup. Only the public contact form will.

- The API checks its own health at two built-in addresses, which Azure uses to restart it if it hangs.

- The database updates itself on start-up. That is fine with one copy running, and it is how I would run it.

- Behind Azure's front door the API must be told it is already on HTTPS, or it can redirect forever. This is one setting I will include.

- Real-time messaging uses a connection to the API. With one copy running it works as is. With several copies, it needs the Redis cache, which is when we would add it.

- The mobile apps are hard-wired to your computer (`localhost`). Release builds must point to `https://api.gosits.com`. The Android setting that allows plain HTTP was only for development and must not ship.

# 4. Monthly cost estimate (Canadian dollars)

Prices below come from Azure's public price list for Canada Central on 26 October 2026, except where marked as an estimate. They are before HST. Azure bills Canadian businesses 13% HST. If the company registers for HST, it can claim that back (see the HST section of your call sheet).

| Item | What it does | Per month | How sure |
| --- | --- | --- | --- |
| Database (PostgreSQL, small size, 32 GB) | Holds every account, booking, message, enquiry | about 24 | Compute 19.13 from Azure's list. Storage about 5 is my estimate. |
| API container (always on) | Runs the backend and its background jobs | about 12 to 18 | Estimate. Azure gives a free monthly allowance that is not counted here. |
| Web app container | Runs app and admin. Can sleep when nobody is using it. | about 0 to 18 | Estimate. Asleep costs almost nothing but the first visitor waits a few seconds. |
| Container registry (Basic) | Stores the packaged app | 7.17 | From Azure's list (0.236 a day) |
| Logs and monitoring | Error and performance records | about 0 | First 5 GB a month free, then 3.91 per GB |
| Key Vault | Keeps passwords and keys safe | about 1 | From Azure's list (0.0425 per 10,000 uses) |
| File storage | Documents and interview recordings | under 1 to start | 0.0283 per GB, from Azure's list. Grows with use. |
| Public website | www.gosits.com | 0 | Free tier, already running |
| Estimated total |  | about 45 to 70 |  |

Optional later: Redis cache 22.78 a month (needed only when running several copies), Service Bus about 15 (not used by the code today).

## Costs that are not Azure

| Service | What to know |
| --- | --- |
| Email mailbox (Microsoft 365) | Per mailbox, per month. GoDaddy shows the exact price at checkout. |
| Outgoing app email (Brevo or similar) | Brevo has a free tier. I have not confirmed its current limits. |
| Video interviews (LiveKit) | Pay by usage with a free starting tier. I have not confirmed current prices. |
| Stripe payments | A fee on every card payment, plus Connect charges for paying caregivers. I could only find US figures ($2 per active caregiver account per month, plus 0.25% and 25 cents per payout). Check stripe.com/ca/connect/pricing. These come out of your 15% commission, so they matter for the commission decision. |
| Certn background checks | Charged per check. One review site lists starting packages around US$10. Confirm with Certn. The vulnerable sector check from police has its own fee. |
| App stores (only if you publish the mobile apps) | Google Play and Apple charge developer fees. Not needed for the web launch. |
| Insurance, accountant, lawyer | Separate. See your call sheet. |

# 5. What is left before parents and caregivers can register

## Technical (I can do these)

- Backend and database online (phase 1).

- App online at app.gosits.com, with working sign-up and sign-in (phase 3).

- Outgoing email working, so verification and password-reset messages actually arrive.

- The contact form (phase 2).

- Admin page to read enquiries and to approve caregiver checks.

- Automatic database backups switched on, plus an alert to you if the API goes down.

- Sign-up switch, so registration can be closed or opened without changing code.

## Business and legal (these are yours)

- Terms of Service and Privacy Policy reviewed by a lawyer and linked from sign-up. The drafts have not been reviewed.

- Caregiver Service Agreement reviewed, and the independent-contractor question answered.

- Insurance bound (see your call sheet).

- Stripe account approved for live payments, and the live keys added.

- HST decision made, and the price display and receipts built to match.

- Commission rate decided. It is a 15% placeholder in the code.

- Background-check route working: Certn live, and a plan for the police vulnerable sector check.

- A person who answers support email and a process for incidents.

- Tax filings up to date. Grants and some partners will ask.

- Website wording reviewed. The home page says every caregiver is background-checked, which should only be said once it is true in practice.

# 6. Connecting Certn (background checks)

I read Certn's public developer documentation, so I can design this now. You said to use it before their approval, then finalise once they approve. That works, because their documentation and testing environment can be used without full account approval, once you have a test key.

## How it works

- When a caregiver starts a background check, our backend sends Certn their email address and the checks to run. Certn emails the caregiver directly to give consent and enter their details. GoSit never handles their sensitive information, which matches the project rule to keep only verification results.

- Certn sends a notification to our backend when the status changes. Every message is signed, so the backend can prove it is really from Certn. The backend also ignores repeats of the same message.

- The backend then fetches the result and records it on the caregiver's verification case. Your staff still make the final decision, the same as today. Certn's answer is evidence, not approval.

- Certn's Canadian servers (`api.ca.certn.co`) keep the data in Canada. Their access key is created in their portal, is shown once, and expires after a year, with email warnings before.

## What I can build now, and what has to wait

| Can build now (from their documentation) | Has to wait for Certn |
| --- | --- |
| The connection that orders checks and reads results | A test key, to confirm it really works |
| The signed-notification receiver, with the handshake Certn requires | Their confirmation of which check names apply to you |
| Storing the result on the verification case for staff review | Your price list |
| Your staff screen showing check progress | Live key, after approval |

## Questions only Certn can answer (add to your vendor call)

- Is the Vulnerable Sector Check available through your current API? Their specification lists one, but it sits in an older section, and they are retiring the older API.

- If it is not, how do customers who work with children handle it? Do you offer a guided way for the caregiver to apply through their own police service?

- Which check names should we order for Canadian identity verification and criminal record, and what do they cost?

- What are the testing-environment web address and test key, and how soon can we have them?

- What is the limit on requests (their documents say 60 a minute), and is that enough for us?

Expect this to stay partly manual for now. Even if Certn does everything, a vulnerable sector check normally comes through police. Your staff may still review an uploaded police result for a while.

# 7. What I need from you

- Go-ahead to create phase 1 in Azure (database, API container, registry, Key Vault), in the same Zeezo Tech subscription and a new resource group. About CAD 45 to 70 a month once phases 1 to 3 are running.

- Confirm the vendor is Certn. You said "Sena", and I assume that means Certn, listed first on your call sheet.

- Private first or open? I recommend deploying with sign-up closed until section 5 is done.

- Contact form: which enquiry types do you want in the drop-down, and who should be emailed when one arrives?

- Mailbox: create hello@gosits.com in GoDaddy so the new form can email you. Also tell me when it exists.

Prices are from Azure's retail price list, queried 26 October 2026, and change over time. Estimates are marked. This is a planning document, not a quote or a commitment. Confirm figures with Azure's pricing calculator before relying on them.